## Project Details
Name
GC99

## Activities
ActivityNo | Activity | Category | SubCategory | Dates_IDC | Dates_IFR | Dates_IFC | Hours_IDC | Hours_IFR | Hours_IFC | Commodities_Concrete | Commodities_Steel
1 | Piperack_PR01_str | Piperack | Superstructure | 2019-03-08 | 2019-03-22 | 2019-04-12 | 105 | 30 | 15 |  | 235
2 | Piperack_PR01_fdn | Piperack | Foundation | 2019-03-01 | 2019-03-15 | 2019-04-05 | 35 | 10 | 5 | 195
3 | Piperack_PR02_str | Piperack | Superstructure | 2019-03-08 | 2019-03-22 | 2019-04-12 | 105 | 30 | 15 |  | 155
4 | Piperack_PR02_fdn | Piperack | Foundation | 2019-03-01 | 2019-03-15 | 2019-04-05 | 35 | 10 | 5 | 125
5 | Piperack_PR03_str | Piperack | Superstructure | 2019-03-15 | 2019-03-29 | 2019-04-19 | 105 | 30 | 15 |  | 75
6 | Piperack_PR03_fdn | Piperack | Foundation | 2019-03-08 | 2019-03-22 | 2019-04-12 | 35 | 10 | 5 | 51
7 | Piperack_PR04_str | Piperack | Superstructure | 2019-03-15 | 2019-03-29 | 2019-04-19 | 105 | 30 | 15 |  | 175
8 | Piperack_PR04_fdn | Piperack | Foundation | 2019-03-08 | 2019-03-22 | 2019-04-12 | 35 | 10 | 5 | 134
9 | Piperack_PR05_str | Piperack | Superstructure | 2019-03-22 | 2019-04-05 | 2019-04-26 | 105 | 30 | 15 |  | 143
10 | Piperack_PR05_fdn | Piperack | Foundation | 2019-03-15 | 2019-03-29 | 2019-04-19 | 35 | 10 | 5 | 124
11 | Piperack_PR06_str | Piperack | Superstructure | 2019-03-22 | 2019-04-05 | 2019-04-26 | 105 | 30 | 15 |  | 198
12 | Piperack_PR06_fdn | Piperack | Foundation | 2019-03-15 | 2019-03-29 | 2019-04-19 | 35 | 10 | 5 | 164

## SubTasks
SubTask | ProgressRatio | CommodityRatio
IDC | 0.4 | 0
IFR | 0.7 | 0
IFC | 1 | 1

## Commodities
Description | Details | Unit
Concrete | M35 | CUM
Steel | A36 | MT

## Deliverables
DeliverableNo | DeliverableTitle | ActivityNo
1067-C-CAL-0001 | CALCULATION FOR PIPERACK PR01 SUPERSTRUCTURE | 1
1067-C-CAL-0002 | CALCULATION FOR PIPERACK PR02 SUPERSTRUCTURE | 3
1067-C-CAL-0003 | CALCULATION FOR PIPERACK PR03 SUPERSTRUCTURE | 5
1067-C-CAL-0004 | CALCULATION FOR PIPERACK PR04 SUPERSTRUCTURE | 7
1067-C-CAL-0005 | CALCULATION FOR PIPERACK PR05 SUPERSTRUCTURE | 9
1067-C-CAL-0006 | CALCULATION FOR PIPERACK PR06 SUPERSTRUCTURE | 11
1067-C-CAL-0007 | CALCULATION FOR PIPERACK PR01 FOUNDATION | 2
1067-C-CAL-0008 | CALCULATION FOR PIPERACK PR02 FOUNDATION | 4
1067-C-CAL-0009 | CALCULATION FOR PIPERACK PR03 FOUNDATION | 6
1067-C-CAL-0010 | CALCULATION FOR PIPERACK PR04 FOUNDATION | 8
1067-C-CAL-0011 | CALCULATION FOR PIPERACK PR05 FOUNDATION | 10
1067-C-CAL-0012 | CALCULATION FOR PIPERACK PR06 FOUNDATION | 12
1067-C-STR-0013 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR01 SUPERSTRUCTURE | 1
1067-C-STR-0014 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR01 SUPERSTRUCTURE | 1
1067-C-STR-0015 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR01 SUPERSTRUCTURE | 1
1067-C-STR-0016 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR01 SUPERSTRUCTURE | 1
1067-C-STR-0017 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR02 SUPERSTRUCTURE | 3
1067-C-STR-0018 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR02 SUPERSTRUCTURE | 3
1067-C-STR-0019 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR02 SUPERSTRUCTURE | 3
1067-C-STR-0020 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR02 SUPERSTRUCTURE | 3
1067-C-STR-0021 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR03 SUPERSTRUCTURE | 5
1067-C-STR-0022 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR03 SUPERSTRUCTURE | 5
1067-C-STR-0023 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR03 SUPERSTRUCTURE | 5
1067-C-STR-0024 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR03 SUPERSTRUCTURE | 5
1067-C-STR-0025 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR04 SUPERSTRUCTURE | 7
1067-C-STR-0026 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR04 SUPERSTRUCTURE | 7
1067-C-STR-0027 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR04 SUPERSTRUCTURE | 7
1067-C-STR-0028 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR04 SUPERSTRUCTURE | 7
1067-C-STR-0029 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR05 SUPERSTRUCTURE | 9
1067-C-STR-0030 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR05 SUPERSTRUCTURE | 9
1067-C-STR-0031 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR05 SUPERSTRUCTURE | 9
1067-C-STR-0032 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR05 SUPERSTRUCTURE | 9
1067-C-STR-0033 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR06 SUPERSTRUCTURE | 11
1067-C-STR-0034 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR06 SUPERSTRUCTURE | 11
1067-C-STR-0035 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR06 SUPERSTRUCTURE | 11
1067-C-STR-0036 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR06 SUPERSTRUCTURE | 11
1067-C-CON-0037 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR01 FOUNDATION | 2
1067-C-CON-0038 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR01 FOUNDATION | 2
1067-C-CON-0039 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR02 FOUNDATION | 4
1067-C-CON-0040 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR02 FOUNDATION | 4
1067-C-CON-0041 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR03 FOUNDATION | 6
1067-C-CON-0042 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR03 FOUNDATION | 6
1067-C-CON-0043 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR04 FOUNDATION | 8
1067-C-CON-0044 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR04 FOUNDATION | 8
1067-C-CON-0045 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR05 FOUNDATION | 10
1067-C-CON-0046 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR05 FOUNDATION | 10
1067-C-CON-0047 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR06 FOUNDATION | 12
1067-C-CON-0048 | GENERAL ARRANGEMENT DRAWING FOR PIPERACK PR06 FOUNDATION | 12